## Sheet1
Work Breakdown | [8 empty] | Status values: | Priority values
Category | Work Item | Status | Priority | Cost (hrs) | Start Date | End Date | Owner | Reviewer | Active | 1
Start screen | Graphics/Logo | Active | 2 | [5 empty] | Cut | 2
Start screen | Hook up buttons to Options, Help, Start | Active | 2 | [5 empty] | Done, not tested | 3
Done, tested
Options Screen | Controls for time or points setting | Active | 1
Options Screen | Return to Start screen | Active | 1
Help Screen | … | Active | 1
End Screen | … | Active | 1
In-Game | Hook up connect / get it working | Active | 3
In-Game | Sprite for circle | Active | 3
In-Game | Sprite for balls | Active | 3
In-Game | Sprite for goals | Active | 3
In-Game | Ball counter | Active | 3
In-Game | Level transition | Active | 2
Project Mgmt | Track progress of team work | Active | 2